## Hoja1
Phase Complete phases really needed in your concrete co-production process | Objective Identify the objectives assigned to a phase | Tasks Identify the tasks associated to an objective | PROBLEM_PROFILES (They are encountered in https://github.com/interlink-project/interlinkers-data/blob/master/problemprofiles/problemprofiles.json) | INTERLINKERs (the problem profiles addressed by INTERLINKERS can be seen at https://demo.interlink-project.eu/catal) | Comments Indicate expected behaviour regarding INTERLINKER recommendations, identify need for new INTERLINKERs that would be useful to carry out this task and which are not available currently in catalogue: https://demo.interlink-project.eu/catal
ENGAGE | Identify stakeholders | Understand the different types of stakeholders
Create a contact list of potential network participants
Create a contact list of potential network participants
| Engage stakeholders | Prepare an engagement plan
Communicate benefit for stakeholders
Engage citizens in the co-refinement process
DESIGN | Focus the service description enhancement problem collaboratively | Collaboratively problem refinement |  | It does nor recommend INTERLINKERS | It does nor recommend INTERLINKERS
|  | Define requirements and constraints for the public service description enhancement |  | It does nor recommend INTERLINKERS
| Service description refinement process specification | Launch Description Augmenter |  | It does nor recommend INTERLINKERS | Description Augmenter has to be recommended
| Sustainability | Understand motivations and incentives
RUN | Monitor continuous crowd refinement process | Link to the Description Augmenter project |  |  | Only service description creator should be able to access the dashboard to accept contents, if such administrator grants rights to other uses, then they should also be able to access it
Review in Servicepedia dashboard user contributions
| Publish report with description enhancements accepted to be processed | Publish enhancement report from Servicepedia
REFINE | Apply refinements | Generate a checklist for improvements |  |  | Correct name of objective, new name of task
Link to content management system (CMS) where changes should be applied
| Publish refined versions of public service description | Link with enhanced version of service description |  |  | Should recommend
Communicate improvements